# GWO SEVO VoiceCast — Step-by-Step Development Order

I recommend developing VoiceCast in 12 sequential stages, starting with fixing and stabilizing the existing application, then building the client portal, billing, and advanced features.

Do not rebuild the existing application. Extend the current Laravel 12 application, reuse its contact, audio, campaign, IVR, and VitalPBX services, and preserve the current approval process.

## Recommended development sequence

## 01

Production Stability & Audio Playback

Critical

1–2 weeks · Critical priority

Fix silent calls, validate HTTP WAV playback, add media-cache diagnostics, test calls, PBX health checks and deployment verification.

## 02

Client Account & Data Isolation Foundation

Critical

1–2 weeks · Critical priority

Introduce client organizations, client-user relationships, scoped data access, ownership policies and account suspension controls.

## 03

Client Registration & Authentication

1–2 weeks · High priority

Email/phone registration, one-time OTP verification, password creation, email-or-phone login, password recovery and account settings.

## 04

Client Portal & Dashboard

1 week · High priority

Client layout, dashboard, navigation, campaign summaries, approval notifications, account profile and role-restricted views.

## 05

Client Contacts, Groups & Imports

1–2 weeks · High priority

Expose existing contacts, groups and CSV/XLSX imports through client-scoped screens; retain duplicate handling and DND.

## 06

Client Audio Library & Existing Approval

1 week · High priority

Client uploads and previews; Pending, Approved and Rejected statuses; internal reviewers retain exclusive approval rights.

## 07

Client Campaign Creation & Scheduling

2–3 weeks · High priority

Client campaign wizard, group selection, approved audio, schedules, test calls, launch checks and client-visible reporting. Hide caller ID selection.

## 08

Pricing, Wallet & Billing Ledger

Critical

2–3 weeks · Critical priority

Rate plans, client balances, credit reservation, answered-call charging, idempotent deductions, transaction history and reconciliation.

## 09

Payment Gateway & Top-Ups

1–2 weeks · High priority

Payment initiation, verified callbacks, wallet funding, payment reconciliation, receipts and failed-payment handling.

## 10

Notifications & Advanced Reporting

2 weeks · Medium priority

In-app bell, client-specific notifications, email/SMS alerts, playback analytics, billing reports and CSV/XLSX exports.

## 11

Advanced Campaign & IVR Features

2–3 weeks · Medium priority

Recurring campaigns, configurable retry reasons, holiday exclusions, IVR simulation, visual editing and richer IVR response analysis.

## 12

External APIs, Webhooks & Commercial Scaling

2–3 weeks · Later priority

Scoped API keys, signed webhooks, usage limits, client commercial plans, external integrations and performance testing.

Durations are provisional development estimates, assuming one experienced Laravel developer with access to the existing codebase, PBX environment and testing resources. Some stages can overlap once their dependencies are complete.

## What to develop inside each stage

### Stage 1 — Production stability (start here)

Your previous testing showed that calls connected but audio playback failed. Fixing this is the first priority.

Development tasks:

- Resolve Asterisk HTTP media-cache and playback failures.

- Add a Test Audio Call action for authorized internal users.

- Verify audio URLs, permissions, checksums, codecs and file availability.

- Add a media delivery health indicator to the dashboard.

- Add clear playback failure reasons to call reports.

- Ensure campaigns cannot dispatch when mandatory media checks fail.

Completion requirement: A controlled test call answers, plays the full approved recording audibly, and reports playback success.

### Stages 2–4 — Build the client foundation

These stages establish the client-facing system without duplicating your internal operations console.

The recommended architecture is:

Internal Admin Portal

Approvals, telephony, billing, monitoring

Client Portal

Contacts, recordings, campaigns, wallet

Shared Laravel Application Services

Permissions · Approval · Contacts · Campaigns · Billing

VitalPBX / Asterisk

Call origination, playback, IVR and telephony events

Before enabling registration, implement account isolation. Every client-facing query and file download must enforce the correct client ownership boundary.

### Stages 5–7 — Deliver the first usable client experience

Build the client workflow in this exact order:

- Client creates a contact group and imports recipients.

- Client uploads a WAV recording.

- Recording enters the existing Pending Approval status.

- Authorized internal approver approves or rejects it.

- Client creates a campaign using the approved recording.

- Client reviews audience, schedule and test-call result.

- Existing technical and compliance launch checks apply.

- Client starts the campaign and monitors outcomes.

At Stage 7, test campaign creation and execution in a restricted environment. Do not launch a paid client service before Stages 8 and 9 are complete, unless a separate approved manual billing arrangement is in place.

### Stages 8–9 — Build billing before commercial launch

The billing ledger should be developed before payment integration because it is the system of record for client balances.

The sequence should be:

Pricing rules → Wallet ledger → Credit reservation → Answered-call charge → Reconciliation → Payment top-up

Keep the documented rule that unanswered calls are not charged. Confirm the monetary meaning of 0.30p, billing duration basis and partial-minute rounding before implementing deductions.

## Delivery milestones

| Milestone | Stages completed | What you can demonstrate |
| --- | --- | --- |
| M1 — Stable Engine | 1 | Successful audio playback and verified PBX integration |
| M2 — Client Access | 2–4 | Secure client registration and dashboard |
| M3 — Client Campaigns | 5–7 | End-to-end client campaign workflow with existing approvals |
| M4 — Commercial MVP | 8–9 | Prepaid wallet, payments and controlled paid campaigns |
| M5 — Enhanced Platform | 10–11 | Notifications, analytics and advanced campaign capabilities |
| M6 — Integration Platform | 12 | External APIs, webhooks and commercial expansion |

## Development checklist

Use this as your implementation tracker.

Implementation progress

0 of 16

Fix HTTP audio playback and verify audible test calls

Implement automated media preflight and health checks

Create client account data model and isolation policies

Implement client registration and OTP verification

Implement password login and client profile

Build client dashboard and navigation

Expose client contacts, groups and imports

Expose audio uploads and existing approval statuses

Build client campaign creation and scheduling

Add approved-audio test call and launch validation

Implement pricing configuration and wallet ledger

Implement answered-call charging and reconciliation

Integrate payment gateway and verified wallet top-ups

Add user-specific notifications and advanced reports

Add recurring campaigns and advanced IVR features

Build APIs, webhooks and commercial integrations

Copy checklist

My recommended immediate development task is Stage 1: Production Stability & Audio Playback. Once the complete call-and-audio path works reliably, move directly to client account isolation, registration, and the client dashboard. That order avoids building a commercial portal on top of an unverified calling engine.